## Sprint 2
Sprint 2 revised backlog
Tasks done | 11 | Estimate (h) | 44
Source: ProductDevelopmentTrack-RequirementsSpec, Sprint 2. Estimates are planned hours; actual hours were not recorded.
Task | Stories | Epic | Work | Est. (h) | Status | Acceptance evidence
B-015 | FR-04 | Candidate Generator | Load one collection’s missing-index hints and preserve source IDs. | 4 | Done | Stored SQL fixture produces 2 CREATE candidates.
B-016 | FR-04, FR-10 | Candidate Generator | Load historical metadata and reset-compatible usage observations. | 4 | Done | No future metadata; stale/reset/missing-baseline checks pass.
B-017 | FR-04 | Candidate Generator | Parse identifiers, merge duplicate hints and suppress covered indexes. | 4 | Done | Escaped identifiers, duplicate merging and coverage tests pass.
B-018 | FR-05 | Scoring Engine | Calculate read benefit from optimizer cost, impact and frequency. | 4 | Done | Orders read benefit 112.8979 heuristic points.
B-019 | FR-05 | Scoring Engine | Calculate separate write, width, storage and maintenance penalties. | 4 | Done | Orders ranks above Events; operational reset checks pass.
B-020 | FR-05, FR-10 | Safety Controller | Reject infeasible candidates and protect critical indexes. | 4 | Done | PK/unique/constraint protection and width/type checks pass.
B-021 | FR-10 | Candidate Generator | Produce conservative redundant/unused-index RETAIN and DROP advice. | 4 | Done | 2 duplicate DROP suggestions; sustained unused-index test passes.
B-022 | FR-05, FR-06 | Feature Store / Workload History | Persist input snapshot, result, policy, engine version and evidence hash. | 3 | Done | SQL-backed result survives a fresh application instance.
B-023 | FR-04, FR-05 | Reporting UI | Expose analysis API and ranked, filterable saved recommendations. | 4 | Done | Action/status/search checks and browser walkthrough pass.
B-024 | FR-06 | Reporting UI | Show advisory SQL, rationale, query evidence, scores and assumptions. | 4 | Done | Browser detail and expanded query evidence verified.
B-025 | All four | Platform / CI-CD | Add unit/API/SQL checks and reproducible acceptance demonstration. | 5 | Done | 140 backend tests, 12 frontend checks and build passed.